{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["项目批复表"],"not_rendered":{"external_links":1,"defined_names":22},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"项目批复表","index":0,"n_rows":17,"n_cols":23,"rows_kept":17,"merged":[[2,0,2,22],[3,0,4,0],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,4,4,4],[3,5,3,7],[3,8,4,8],[3,9,3,12],[3,13,4,13],[3,14,4,14],[3,15,3,19],[3,20,3,22]],"flags":["formulas_cached_only"]}
[]
["附件"]
["石城县2022年第四批巩固拓展脱贫攻坚成果同乡村振兴有效衔接项目计划批复表"]
["序号","项目类别","项目名称","建设性质(新建/续建)","时间进度\n(建设起止年月)","实施地点",null,null,"建设任务（内容）","资金规模和筹资方式",{"$nulls":3},"补助标准","资金来源","绩效目标",{"$nulls":4},"责任单位"]
[{"$nulls":5},"乡（镇）","村","是否重点帮扶村",null,"总投资(万元)","其中：财政衔接推进乡村振兴补助资金","其中：整合财政涉农资金","其中:其他资金",null,null,"效益指标（带农联农效果）","产出指标\n（项目产出成果）","受益\n户数\n（户）","受益\n人口数\n（人）","满意度指标(≥%)","项目主管单位","项目实施单位","后续管护单位"]
["合计",{"$nulls":8},6695.58,1961.58,426.42,4307.58]
["木兰乡",{"$nulls":8},20,20,0,0]
[1,"产业项目","木兰乡田江村集体经济-农机购置项目","新建","2022年01月-2022年12月","木兰乡","田江村","省重点帮扶村","购置农机2台（翻耕机1台、收割机一台）",20,20,0,0,"按石巩固成果字〔2021〕18号文件执行","市级专项资金","可提高农户种植积极性，帮助农户发展粮食、烟叶生产，可扩大种粮面积30亩以上、种烟面积30亩以上，农户户均收入提高1000元以上，村集体经济每年增收12000元以上。","购买翻耕机1台、收割机一台",20,105,95,"县农业农村局","木兰乡人民政府","田江村"]
["大由乡",{"$nulls":8},4,4,0,0]
[2,"基础设施","大由乡大由村旗杆岭电排建设","新建","2022年01月-2022年12月","大由乡","大由村","省重点帮扶村","卧式离心泵扬程30米一台、口径PE管110*长120米。水渠40cm*40cm长90米,PE球阀、PE三通、弯头、法兰；电缆线、漏电断路器、配电箱等",4,4,0,0,"按石巩固成果字〔2021〕18号文件执行","市级专项资金","解决基本农田灌溉2300亩，确保粮食种植生产稳定","离心泵1台，PE管道120m，水渠长90m",732,2915,97,"县农业农村局","大由乡人民政府","大由村"]
["珠坑乡",{"$nulls":8},4600,500,0,4100]
[3,"基础设施","珠坑乡示范乡镇建设一期项目工程","新建","2022年01月-2022年12月","珠坑乡","珠坑村","否","地面破拆8000平米，道路硬化3500平米，水稳层2800平米，余坪硬化12000平米，人行道3000平米，外环路建设5600平米，道路拓宽760平米，排水、排污、给水管道埋设。",4600,500,0,4100,"按石巩固成果字〔2021〕18号文件执行","市级专项资金","结合示范乡镇建设，改善圩镇及周边路网配套设施及排水排污，完善基础功能，美化圩镇环境","地面破拆8000平米，道路硬化3500平米，水稳层2800平米，余坪硬化12000平米，人行道3000平米，外环路建设5600平米，道路拓宽760平米，排水、排污、给水管道埋设。",890,4800,98,"县农业农村局","珠坑乡人民政府","珠坑乡人民政府"]
["农业农村局",{"$nulls":8},911.58,911.58,0,0]
[4,"产业项目","大棚蔬菜产业发展奖补项目","新建","2022年01月-2022年12月","全县","田心村、东坑村、沿沙村、桐江村、江背村、塘台村、平阳村、友联村、新龙村、大由村、亨田村等","部分","用于高田镇田心村、木兰乡东坑村、丰山乡沿沙村、小松镇桐江村、琴江镇江背村、珠坑乡塘台村、横江镇平阳村、赣江源镇友联村、龙岗乡新龙村、大由乡大由村、屏山镇亨田村等地建设大棚蔬菜基地奖补，面积约1400亩。",700.85,700.85,0,0,"按石巩固成果字〔2021〕18号文件执行","市级专项资金","基地辐射带动全县发展大棚蔬菜6000余亩，解决务工人员约1200人，增加菜农户均收入5000元以上","奖补大棚蔬菜基地面积约1400亩",350,1575,98,"县农业农村局","石城县赣江源农业发展有限公司","石城县赣江源农业发展有限公司"]
[5,"产业项目","全县种粮农民一次性补贴及粮食生产先进奖励项目","新建","2022年01月-2022年12月","各乡镇","各村","部分","按照全县粮食播种面积39.49万亩、粮食产量12.5万吨目标任务的种粮农户一次性补贴及对粮食生产先进乡(镇)、村、种植大户、先进工作者进行奖励",210.73,210.73,0,0,"按石巩固成果字〔2021〕18号文件执行","市级专项资金","提高农户种粮积极性，增加种粮农户补贴收入，为全国粮食生产战略部署提供保障措施","粮食播种面积39.49万亩、粮食产量12.5万吨",20500,92250,98,"县农业农村局","县农业农村局"]
["烟草专卖局",{"$nulls":8},1160,526,426.42,207.58]
[6,"产业项目","全县k326品种中上等烟扶持项目","新建","2022年01月-2022年12月","各乡镇","各村","部分","扶持约1100户发展烟叶产业（k326品种中上等烟580万斤），每斤补助2元",1160,526,426.42,207.58,"按有关文件执行","市级专项资金","促进烟草产业发展，年增加县税收收入1700余万元，可使约1100户种植户户均增收6.5万元以上","产出k326品种中上等烟叶约580万斤",1100,5500,97,"县烟草局","县烟草局"]