{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["第六批项目计划表"],"not_rendered":{"external_links":3,"defined_names":5},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"第六批项目计划表","index":0,"n_rows":58,"n_cols":21,"rows_kept":58,"merged":[[1,0,1,20],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,2,7],[2,8,2,10],[2,11,3,11],[2,12,2,18],[2,19,3,19],[2,20,3,20]],"flags":["formulas_cached_only"]}
["附件"]
["石城县2025年第六批巩固拓展脱贫攻坚成果同乡村振兴有效衔接项目计划批复公告表"]
["序号","项目类别","项目名称","建设性质（新建/改建/扩建）","实施期限\n（建设起止年月）","实施地点",null,null,"资金规模和筹资方式",null,null,"资金来源","绩效目标",{"$nulls":6},"责任\n单位","资产后续管护单位"]
[{"$nulls":5},"乡（镇）","村、组","是否重点帮扶村","总投资（万元）","其中：财政衔接推进乡村振兴补助资金","其中：其他资金",null,"项目建设内容及规模","效益指标\n（含联农带农富农机制）","其中：\n受益\n村数\n（个）","其中：\n受益\n户数\n（户）","其中：\n受益\n人口数\n（人）","其中：受益脱贫户和三类人群数","满意度指标（≥）"]
["合计",{"$nulls":7},1062,1062,0]
["高田镇",{"$nulls":7},39,39,0]
[1,"乡村建设","高田村江下、赖田、园门、中井、丰坪农田灌溉设施建设项目","新建","2025年01月-2025年12月","高田镇","高田村","否",23,23,0,"市级专项资金","1、新建混泥土水渠，0.4米*0.4米*0.1米，长约1500. 2新建混泥土水渠0.8米*0.8米120米","可解决270余亩农田灌溉问题，促进120户群众增收",1,150,630,210,{"v":0.95,"d":"95%"},"县农业农村局","高田村村委会"]
[2,"乡村建设","高田镇礼地村老屋组村庄整治","新建","2025年01月-2025年12月","高田镇","礼地村","县重点帮扶村",16,16,0,"市级专项资金","空坪硬化610㎡，浆砌石298m³，排水沟20*20*9cm40m,40*40*10cm100m，2个水塘清淤，环境整治等","可改善30户村民生活居住条件",1,30,110,15,{"v":0.95,"d":"95%"},"县农业农村局","礼地村村委会"]
["丰山乡",{"$nulls":7},47,47,0]
[1,"乡村建设","丰山乡大琴村店下组、茶山组、红卫组村庄整治项目","新建","2025年01月-2025年12月","丰山乡","大琴村","否",20,20,0,"市级专项资金","1.内径800mm混凝土涵管长12m，内径400mm，长26m；\n2.浆砌石挡土墙约360立方米；\n3.空坪硬化，红卫组、山下组约360平方米；\n4.混泥土污水沟30㎝×30㎝*10㎝长约150米；\n5.混泥土污水沟40㎝×40㎝*10㎝长约250米。","方便群众出行，改善基础设施",1,66,356,21,{"v":0.97,"d":"97%"},"县农业农村局","大琴村村委会"]
[2,"乡村建设","丰山乡沿沙村新街组村庄整治项目","新建","2025年01月-2025年12月","丰山乡","沿沙村","县重点帮扶村",20,20,0,"市级专项资金","1.破旧路面挖除约240立方米；\n2.路面修复，C20混凝土面层，厚20cm约修复约1300㎡；\n2.40*40排水沟约420米；","方便群众出行，改善基础设施",1,77,314,18,{"v":0.95,"d":"95%"},"县农业农村局","沿沙村村委会"]
[3,"乡村建设","石城县丰山乡河田村琴溪组村庄整治项目","新建","2025年01月-2025年12月","丰山乡","河田村","是",7,7,0,"市级专项资金","1.混凝土沟渠60cm*60cm*10cm，长40米，及配套沟盖板；\n2.混凝土沟渠40cm*40cm*10cm，长130米，及配套沟盖板；\n3.空坪硬化约300平方米；\n4.太阳能路灯5盏。\n\n","提升琴溪小组人居环境及村容村貌",1,48,202,30,{"v":0.96,"d":"96%"},"县农业农村局","河田村委会"]
["木兰乡",{"$nulls":7},20,20,0]
[1,"乡村建设","木兰乡木兰村樟树下至礼堂组周边村庄整治项目","新建","2025年01月-2025年12月","木兰乡","木兰村","省重点帮扶村",20,20,0,"市级专项资金","空坪硬化325㎡，排水沟70米（0.3*0.3）米，DN500涵管40m，挡墙520m³等","改善人居环境，滑坡问题，提升群众满意度。",1,42,146,9,{"v":0.95,"d":"95%"},"县农业农村局","木兰村村委会"]
["小松镇",{"$nulls":7},63.5,63.5,0]
[1,"乡村建设","小松镇丹溪村甘陂段村庄整治项目","新建","2025年01月-2025年12月","小松镇","丹溪村甘陂段","县重点帮扶村",10.5,10.5,0,"市级专项资金","屋檐及空坪硬化260平方，40*40cm水沟60米，挡土墙240立方等","提升村容村貌，改善脱贫（监测）户16户57人生产生活条件；",1,86,326,57,{"v":0.95,"d":"95%"},"县农业农村局","丹溪村委会"]
[2,"乡村建设","小松镇胜和村大燕里至富溪村庄整治项目","新建","2025年01月-2025年12月","小松镇","胜和村富溪组","否",6.3,6.3,0,"市级专项资金","富溪组空坪硬化400㎡，小河边浆砌石挡土墙长12米*高2.2米*宽1米，进富溪公路浆砌石挡土墙长10米*高3米*宽1米等","提升村容村貌，解决脱贫（监测）户2户12人安全出行,改善生产生活条件；",1,17,74,118,{"v":0.95,"d":"95%"},"县农业农村局","胜和村村委会"]
[3,"乡村建设","小松镇迳里村横坵小组道路、水渠建设项目","新建","2025年01月-2025年12月","小松镇","迳里村横坵组","县重点帮扶村",10.7,10.7,0,"市级专项资金","道路硬化约1050㎡，18CM厚C20混凝土面层，10cm厚砂砾垫层等","解决脱贫（监测）户4户16人生产出行问题,改善生产条件；",1,17,98,16,{"v":0.95,"d":"95%"},"县农业农村局","迳里村村委会"]
[4,"产业项目","小松镇迳里村养猪场配套设施项目","新建","2025年01月-2025年12月","小松镇","迳里村横坵组","县重点帮扶村",3,3,0,"市级专项资金","新建砖砌堆肥房约100㎡，含地面10CM厚C20混凝土面层硬化、1米高砖砌墙、有机透明塑料瓦屋面，排水沟100米等","助力产业发展，增加村集体经济收入0.18万元/年，收益用于公益性岗位、小型公益事业，惠及301户农户2208人",1,301,2208,213,{"v":0.95,"d":"95%"},"县农业农村局","迳里村村委会"]
[5,"乡村建设","小松镇新华村陈地护坡建设项目","新建","2025年01月-2025年12月","小松镇","新华村陈地","否",20,20,0,"市级专项资金","浆砌石长53m*高6m宽2m等","解决脱贫（监测）户8户37人安全出行,改善生产生活条件；",1,42,205,37,"98%","县农业农村局","新华村村委会"]
[6,"乡村建设","小松镇江口村新建陈坑里水陂水渠项目","新建","2025年01月-2025年12月","小松镇","江口村、底下屋","否",13,13,0,"市级专项资金","水陂长10m*高4m*底宽3.5米，顶宽2m,两边八字墙共30m*高2m*宽1m，40*40cm水渠280米等","解决脱贫户（监测户）12户48人250亩农田水利灌溉问题，改善生产条件，增产增收；",1,110,336,48,{"v":0.97,"d":"97%"},"县农业农村局","江口村村委会"]
["琴江镇",{"$nulls":7},67.6,67.6,0]
[1,"乡村建设","琴江镇长天村虎眼里基础设施建设","新建","2025年01月-2025年12月","琴江镇","长天村","否",8.6,8.6,0,"市级专项资金","路面改造约50㎡、40*40cm水渠约30米、新建挡土墙约152m³等基础设施。","保护公路，给村民带来出行方便",1,34,104,16,{"v":0.97,"d":"97%"},"县农业农村局","长天村村委会"]
[2,"乡村建设","琴江镇兴隆村硬田咀村庄整治","新建","2025年01月-2025年12月","琴江镇","兴隆村","否",20,20,0,"市级专项资金","空坪硬化800㎡，道路硬化600㎡；浆砌石挡墙长150m，上宽0.8m，底宽1.5m，高2m；30*30cm排水沟200m等。","改善人居环境条件，提升群众满意度。",1,56,168,14,{"v":0.97,"d":"97%"},"县农业农村局","兴隆村村委会"]
[3,"乡村建设","琴江镇古樟村石昌小组桥梁建设","新建","2025年01月-2025年12月","琴江镇","古樟村","否",39,39,0,"市级专项资金","桥梁建设13m，桥面5.5米宽，河道跨度13米长，八字墙长5m、宽1m、高7m","项目完工后利于防洪排水，保障石昌组、蛇头组村民房屋安全及出行安全问题，保障村民生命财产安全，防止100余亩农田因排水不畅导致受灾",1,61,245,18,{"v":0.97,"d":"97%"},"县农业农村局","古樟村村委会"]
["屏山镇",{"$nulls":7},56,56,0]
[1,"乡村建设","屏山镇河东村井边组村庄整治项目","新建","2025年01月-2025年12月","屏山镇","河东村","县重点帮扶村",20,20,0,"市级专项资金","1.新建太阳能路灯20盏；\n2.C20 混凝土面层，18CM 厚1000㎡；3.透水砖地面500㎡等","完善基础设施，增加群众获得感和幸福感",1,46,132,23,0.98,"县农业农村局","河东村村委会"]
[2,"乡村建设","屏山镇页背村大排组村庄整治项目","新建","2025年01月-2025年12月","屏山镇","页背村","县重点帮扶村",20,20,0,"市级专项资金","1.地面硬化(原土碾压，砂砾\n找平，18CM 混泥土面)1800㎡；2.新建太阳能路灯20盏；3.透水砖地面550㎡","完善基础设施，增加群众获得感和幸福感",1,55,155,33,0.98,"县农业农村局","页背村村委会"]
[3,"乡村建设","屏山镇屏山村枫树、书院、米坪、街上等小组路灯安装项目","新建","2025年01月-2025年12月","屏山镇","屏山村","是",16,16,0,"市级专项资金","安装太阳能路灯200盏。","改善村民生活条件和基础环境,可有效改善全镇村民安全出行、改善生产条件。",1,1511,5126,316,{"v":0.98,"d":"98%"},"县农业农村局","屏山村村委会"]
["大由乡",{"$nulls":7},46,46,0]
[1,"乡村建设","大由乡水南村里村、旗形排片区水渠建设项目","新建","2025年01月-2025年12月","大由乡","水南村","县重点帮扶村",18,18,0,"市级专项资金","里村新建水渠40cm*40cm长1000m；旗形排新建水渠30cm*30cm长200m","农田水利：解决脱贫（监测）户45户381人100亩农田水利灌溉问题，改善生产条件，增产增收；",1,465,2325,381,"98%","县农业农村局","水南村村委会"]
[2,"乡村建设","大由乡王沙村石舍至坳上水渠修复建设项目","新建","2025年01月-2025年12月","大由乡","王沙村石舍至坳上","县重点帮扶村",18,18,0,"市级专项资金","王沙村石舍至坳上新建水渠1m*1m长358米、pe管110mm铺设长780米。","解决脱贫（监测）户20户80人100亩农田水利灌溉问题，改善生产条件，增产增收；",1,60,420,80,"98%","县农业农村局","王沙村村委会"]
[3,"乡村建设","大由乡下伊村旱坑组水渠、水陂建设项目","新建","2025年01月-2025年12月","大由乡","下伊村旱坑组","否",10,10,0,"市级专项资金","大由乡下伊村旱坑组新建水陂一座，长4米，宽1.2米，高2米，c20混凝土挡土墙浇筑7立方米，新建40cm*40cm水渠长400m，新建c20混凝土水陂防渗面板长6米，宽0.2米，高2米，c20混凝土浇筑2.4立方米。","解决脱贫（监测）户9户42人40亩农田水利灌溉问题，",1,12,97,42,"98%","县农业农村局","下伊村村委会"]
["龙岗乡",{"$nulls":7},43.5,43.5,0]
[1,"乡村建设","龙岗乡新龙村前门、后门组村庄整治项目","新建","2025年01月-2025年12月","龙岗乡","新龙村","县重点帮扶村",20,20,0,"市级专项资金","空坪硬化600㎡，30*30排水沟300米，浆砌石200立方米，路灯20盏等基础设施。","提升村容村貌，改善生产生活条件，完善村庄基本公共设施，助力乡村旅游发展。",1,122,414,20,{"v":0.97,"d":"97%"},"县农业农村局","新龙村村委会"]
[2,"乡村建设","龙岗乡下迳村河背、新屋组村庄整治项目","新建","2025年01月-2025年12月","龙岗乡","下迳村","县重点帮扶村",20,20,0,"市级专项资金","空坪硬化158㎡，30*30排水沟282米，30*30水沟盖板282米，路灯20盏，河提浆砌石300立方米等基础设施。","提升村容村貌，改善生产生活条件，完善村庄基本公共设施，助力乡村旅游发展。",1,54,272,20,{"v":0.97,"d":"97%"},"县农业农村局","下迳村村委会"]
[3,"乡村建设","龙岗乡下迳村破坑村庄整治项目","新建","2025年01月-2025年12月","龙岗乡","下迳村","县重点帮扶村",3.5,3.5,0,"市级专项资金","道路硬化350㎡等基础设施。","提升村容村貌，改善生产生活条件，完善村庄基本公共设施。",1,45,148,12,{"v":0.97,"d":"97%"},"县农业农村局","下迳村村委会"]
["赣江源镇",{"$nulls":7},31.54,31.54,0]
[1,"乡村建设","赣江源镇罗云村双旗栋道路整治","新建","2025年01月-2025年12月","赣江源镇","罗云村","省重点帮扶村",2.5,2.5,0,"市级专项资金","路面破除147.7㎡；路面硬化147.7㎡；c20混泥土沟盖板12cm厚2.1504m³；M10浆砌石挡土墙3.78m³；C15 混泥土垫\n层1.2m³；混凝土涵管埋\n设内径 300MM，4m。","消除路面安全隐患，解决水渠排水不畅问题",1,180,562,108,{"v":0.95,"d":"95%"},"县农业农村局","罗云村村委会"]
[2,"乡村建设","赣江源镇洋地村村庄整治项目","新建","2025年01月-2025年12月","赣江源镇","洋地村","县重点帮扶村",6.54,6.54,0,"市级专项资金","1.长布组污水处理沉沙井3个，污水管道新建300m。\n","可以解决对应小组污水处理，搞好环境卫生，提升群众满意度",1,21,97,5,{"v":0.95,"d":"95%"},"县农业农村局","洋地村村委会"]
[3,"乡村建设","赣江源镇罗云村营背前道路路灯安装项目","新建","2025年01月-2025年12月","赣江源镇","罗云村","省重点帮扶村",6,6,0,"市级专项资金","罗云村营背前道路路灯安装30盏","改善夜间照明，方便群众出行",1,200,1350,323,{"v":0.95,"d":"95%"},"县农业农村局","罗云村村委会"]
[4,"乡村建设","赣江源镇石溪村温坑背水渠、水陂建设项目","新建","2025年01月-2025年12月","赣江源镇","石溪村","否",6.5,6.5,0,"市级专项资金","水渠40cm*40cm*10cm约300m，混凝土水陂1座,长5m、宽2.5m、高2m（需二次搬运）等。","灌溉温坑背农田20亩，促进农业产业发展",1,30,118,62,{"v":0.95,"d":"95%"},"县农业农村局","石溪村村委会"]
[5,"乡村建设","赣江源镇洋和村茶山塘","新建","2025年01月-2025年12月","赣江源镇","洋和村","否",10,10,0,"市级专项资金","茶山塘塘埂长60米，混泥土护塘坝高3米，厚40厘米，斜涵1只，排水渠长120米（30*30），清淤120立方，人口260余人。","涉及灌溉农田面积约90余亩",1,50,201,52,{"v":0.95,"d":"95%"},"县农业农村局","洋和村村委会"]
["横江镇",{"$nulls":7},95.6,95.6,0]
[1,"乡村建设","横江镇小姑村大坝组道路建设项目","新建","2025年01月-2025年12月","横江镇","小姑村","县重点帮扶村",20,20,0,"市级专项资金","大坝组修复破损路面1700m2及配套排水涵管、PVC排水管等，30cm*30cm盖板水沟约100米等","解决脱贫（监测）户25户108人人居环境问题，改善人居环境和出行条件。",1,25,108,3,{"v":0.97,"d":"97%"},"县农业农村局","小姑村村委会"]
[2,"乡村建设","横江镇烟坊村江背组道路硬化项目","新建","2025年01月-2025年12月","横江镇","烟坊村","县重点帮扶村",20.1,20.1,0,"市级专项资金","江背组道路硬及场地硬化约2150m2；30*30水沟60m等。","解决脱贫（监测）户10户48人安全出行,改善生产生活条件。",1,59,188,10,{"v":0.98,"d":"98%"},"县交通局","烟坊村村委会"]
[3,"乡村建设","横江镇张坑村赖屋排及张子坑等组村庄整治项目","新建","2025年01月-2025年12月","横江镇","张坑村","县重点帮扶村",23,23,0,"市级专项资金","赖屋排小组空坪硬化约200m2，新建挡土墙约70m3，30cm*30cm水沟约40m；张子坑小组新建挡土墙约500m3等","解决脱贫（监测）户8户27人人居环境问题，改善人居环境条件。",1,35,186,8,{"v":0.98,"d":"98%"},"县农业农村局","张坑村村委会"]
[4,"乡村建设","横江镇姑溪村新屋等组猪本坑机耕道及水渠项目","新建","2025年01月-2025年12月","横江镇","姑溪村","县重点帮扶村",{"v":21,"d":"21.0"},{"v":21,"d":"21.0"},0,"市级专项资金","新屋组新建机耕道长约1100m*宽3.5m，含铺设内径30cm涵管长度22m、80cm内径涵管长度41m;新建水渠长约900m*宽40cm*高40cm等。兰家屋组DN400闸阀1处等","社会效益，满足沿线群众生产运输,带动20户农户增加水稻种植面积59亩",1,46,199,7,{"v":0.98,"d":"98%"},"县农业农村局","姑溪村委会"]
[5,"乡村建设","横江镇和平村王苟排李家边陈家屋等组村庄整治项目","新建","2025年01月-2025年12月","横江镇","和平村","否",11.5,11.5,0,"市级专项资金","王苟排小组道路扩宽280米，宽1米；混凝土挡土墙约60m3，砌砖长22米，高0.6米，约7m3砌砖；王苟排，李家边，陈家屋等小组立式路灯17盏，挂式路灯3盏；涵管直径40厘米，长18米（含18米水泥硬化）等","解决脱贫（监测）户13户190人安全出行,改善生产生活条件。",1,58,190,13,{"v":0.98,"d":"98%"},"县农业农村局","和平村村委会"]
["珠坑乡",{"$nulls":7},76.26,76.26,0]
[1,"乡村建设","珠坑乡珠坑村欧里村庄整治","新建","2025年01月-2025年12月","珠坑乡","珠坑村、欧里组","否",42,42,0,"市级专项资金","余坪及道路硬化2500㎡，护坡190米，涵管20m，泥土清运530方。","人居环境整治：解决脱贫（监测）户22户87人人居环境问题，改善人居环境条件",1,98,485,87,"96%","县农业农村局","珠坑村村民委员会"]
[2,"乡村建设","珠坑乡良溪村祠堂、水口、新付挡土墙建设","新建","2025年01月-2025年12月","珠坑乡","良溪村新付、里楼、石胜前、祠堂、水口","县重点帮扶村",11.26,11.26,0,"市级专项资金","祠堂、水口、新付三处挡土墙修建，共计391立方米","解决脱贫（监测）户72户433人60余亩农田安全隐患问题，改善生产条件，增产增收；",1,513,2035,433,{"v":0.96,"d":"96%"},"县农业农村局","良溪村村民委员会"]
[3,"乡村建设","珠坑乡竹溪村里岩、大屋里、黄金坑村庄整治建设","新建","2025年01月-2025年12月","珠坑乡","竹溪村里岩，黄金坑，岭坑","县重点帮扶村",23,23,0,"市级专项资金","1.里岩浆砌石护坡1长65米高5米，路沿护坡2长30米高3.5米；\n2.水泥路硬化长20米宽3.5米；                              3.大屋里道路空坪硬化150平方；\n4.黄金坑、里岩、观塘下空坪硬化680平方","解人居环境整治：解决脱贫（监测）户22户62人人居环境问题，改善人居环境条件",1,92,435,85,"96%","县农业农村局","竹溪村村民委员会"]
["县农业农村局",{"$nulls":7},446,446,0]
[1,"产业项目","全县蔬菜产业发展奖补项目","新建","2025年01月-2025年12月","所涉乡镇","所涉村","部分",315,315,0,"市级专项资金","全县大棚蔬菜基地更新换膜建设奖补约1000亩等。","带动脱贫户72户种植蔬菜，基地劳务用工脱贫户138人就业，户平增收4.8万元。",18,261,960,161,{"v":0.96,"d":"96%"},"县农业农村局"]
[2,"乡村建设","全县农村人居环境长效管护项目","新建","2025年01月-2025年12月","各乡镇","131个村","部分",131,131,0,"市级专项资金","全县131个村的农村人居环境整治，主要用于村庄道路、村庄沿线环境整治，污水治理及垃圾清扫等。","改善131个行政村村庄人居环境面貌，提升群众生产生活幸福指数及满意度。",131,51000,203610,51000,{"v":0.95,"d":"95%"},"县农业农村局"]
["县果茶发展服务中心",{"$nulls":7},30,30,0]
[1,"产业项目","石城县改建高标准茶叶基地奖补项目","改建","2025年01月-2025年12月","琴江镇","长乐村","县重点帮扶村",30,30,0,"市级专项资金","对长乐村原茶叶基地进行高标准改造奖补，面积约100亩，奖补资金不超过项目总投资30%（主要提升改造基地相关设施，新增灌溉系统设备；修建道路系统，基地内主干道、作业道改建；建设防护林带；购置采茶、制茶加工及包装设备等，具体奖补标准及要求详见奖补实施方案）。","项目建成后可带动86户农户增收，户均增收2600 元 ，新增就业10人，受益总人口达488人，其中受益脱贫户和监测对象数26人。",1,86,488,26,{"v":0.95,"d":"95%"},"县果茶服务中心","农林水企业"]